## Slide 1
medical_services
Clinic Management System
CLINIC OS
Next-Gen Care Delivery
Project Proposal Presentation
Prepared for the Client

## Slide 2
1. What We're Building
web
Web-Based System
A single integrated system replacing outdated manual registers.
person_add
Patient Registration
Seamless patient onboarding and advanced search capabilities.
confirmation_number
Token Generation
Efficient doctor slip and digital queue token generation.
payments
Billing & Receipts
Integrated billing for Lab, X-Ray, ECG, ECO, and Ultrasound.
meeting_room
Operation Theater
Streamlined room booking and comprehensive final billing.
dashboard
Management Portal
Real-time tracking of cash, clinical performance, and expenses.
settings
Direct Management
Easy configuration of doctors, tests, and standard pricing.
security
Secure Logins
Role-based access security for staff and management.

## Slide 3
2. Work & Cost Breakdown
payments
Total Fixed Price
PKR 60,000
schedule
Total Work Hours
300 hrs
Key Modules Included
check_circlePatient & Doctor Registration
check_circleBilling Counters (Lab, X-Ray, ECG, etc.)
check_circleOperation Theater Module
check_circleExpenses, Salaries & Reports
check_circleTesting, Optimization & Training

## Slide 4
3. Accelerated 2-Week Timeline
Delivery Speed
14 Days
Extremely fast-tracked delivery compared to typical 10-12 weeks.
groups
Requires active parallel work by 3-4 developers and prompt client feedback.
Days 1-2
Setup, UI design & Patient Reg.
Days 3-5
Doctor Reg & all 5 Billing Counters
Days 6-9
OT module, Test management & Expenses
Days 10-12
Dashboard, Optimization & Full Testing
Days 13-14
Fixes, Training, and Handover

## Slide 5
4. Payment Schedule
payments
Total Project Cost
PKR 60,000
Payment Structure
Milestone-Based
Payments are structured around key deliverables to ensure rapid and transparent project progress.
30%
1. Advance (Kick-off)
PKR 18,000
40%
2. Mid-project (Day 7) - PKR 24,000
adjustMilestone: Patient Reg, Doctor slip, Billing working.
30%
3. Final Payment (Day 14) - PKR 18,000
adjustMilestone: Completion, testing, handover & training.

## Slide 6
5. Scope Clarifications
INCLUDED IN PROJECT
check_circleFully built & tested system Complete software delivery representing 300 hours of development.
check_circle1 Month free maintenance Post-deployment support including quick bug fixes & stability updates.
check_circleStaff training & user guide Hands-on guidance for operators and complete documentation.
EXCLUDED / ADDITIONAL
cancelCloud server, domain & SSL Hosting infrastructure setups are provided and paid directly by client.
cancelDeployment charges Final deployment setup and server configuration are billed separately.
cancelNew features after sign-off Post-agreement scope changes (e.g., SMS alerts, dedicated mobile app).

## Slide 7
6. Before We Start
Required Confirmations
payment
Payment Methods
Cash only or Card/Bank?
print
Printer Type for Receipts
Small receipt printer or standard A4?
dns
Cloud Server Details
Required credentials/details for deployment and testing.
System Setup Note
cloud_done
Direct Registration
Management registers real data (doctors and prices) inside the system directly.
No need to prepare lists in advance