Clinic Management System — Project Proposal

1. What We're Building

A single web-based system for your clinic that replaces manual registers with:

- Patient registration & search

- Doctor slip / token generation for each patient visit

- Billing & receipts for Laboratory, X-Ray, ECG, ECO (Echo) and Ultrasound

- Operation Theater booking, room/bed management, and final billing

- A management dashboard showing daily/weekly/monthly cash, doctor performance, and expenses

- Doctor, employee, and price-list management screens — Management adds doctors and every test/price directly inside the system whenever needed; nothing is fixed in advance or needs to be handed over to us

- Secure logins for staff (Operator) and clinic owner/admin (Management)

2. Work & Cost Breakdown

The total price is fixed at PKR 60,000, split below by feature so you can see exactly what your money is paying for.

| # | Feature | What it does for you | Work Hours | Cost |
| --- | --- | --- | --- | --- |
| 1 | Project setup & screen design | Planning the app and designing every screen so it's easy to use | 20 | 4,000 |
| 2 | Staff login & permissions | Separate secure logins for counter staff and management | 10 | 2,000 |
| 3 | Patient registration & search | Add new patients, auto-generate MR number, search old patients instantly | 20 | 4,000 |
| 4 | Doctor registration & doctor slip/token | Add doctors, generate the token slip patients get after seeing the doctor | 25 | 5,000 |
| 5 | Laboratory billing & receipts | Counter screen to bill and print lab test receipts | 15 | 3,000 |
| 6 | X-Ray billing & receipts | Counter screen to bill and print X-Ray receipts | 12 | 2,400 |
| 7 | ECG billing & receipts | Counter screen to bill and print ECG receipts | 12 | 2,400 |
| 8 | ECO billing & receipts | Counter screen to bill and print ECO receipts | 12 | 2,400 |
| 9 | Ultrasound billing & receipts | Counter screen to bill and print Ultrasound receipts | 12 | 2,400 |
| 10 | Operation Theater module | Room/bed booking, procedure & medicine tracking, final OT bill | 40 | 8,000 |
| 11 | Test & price list management | Screens for management to add/update tests and prices anytime | 15 | 3,000 |
| 12 | Expenses, salaries & doctor payments | Record salaries, doctor payouts, and daily/monthly clinic expenses | 15 | 3,000 |
| 13 | Management dashboard & reports | Cash summary, doctor-wise & department-wise reports, with export | 25 | 5,000 |
| 14 | Employee records | Simple staff records used for salary payments | 8 | 1,600 |
| 15 | Speed optimization | Making frequently-used screens (prices, doctor list, dashboard) load instantly | 8 | 1,600 |
| 16 | Testing & bug fixing | Making sure everything works correctly before handover | 31 | 6,200 |
| 17 | Staff training & user guide | Hands-on training for your team + a simple how-to guide | 10 | 2,000 |
| 18 | Project coordination | Progress updates and meetings throughout the project | 10 | 2,000 |
|  | Total |  | 300 hrs | PKR 60,000 |

Note: Items 5 - 9 (Laboratory, X-Ray, ECG, ECO, Ultrasound) look similar to each other by design once the first one is built, the rest reuse the same pattern, which is why they cost less individually.

3. What's Included

- Everything in the table above, fully built and tested

- 1 month of free maintenance after handover; covers fixing anything that doesn't work as described in the requirement document

- Staff training and a basic user guide

4. What's NOT Included

- Deployment charges (installing and setting up the system on your cloud server, domain, SSL certificate), quoted and billed separately; the cloud server itself will be provided by you (the client)

- Any new feature or change requested after this proposal is signed off (see below)

- Ongoing cloud/server bills; since you're providing the cloud server, these are paid directly by you to your cloud provider, not part of this cost

5. After the Free Month: Maintenance & New Features

- First month after handover: Free covers bug fixes only (something not working as agreed).

- After the first month / any new feature: Charged separately. Examples: SMS reminders, insurance module, multi-branch support, mobile app, or anything not listed in Section 2 above.

  - New work will be quoted at the same rate used in this proposal (PKR 200/hour, ≈ 60,000 ÷ 300 hrs), or as a fixed quote for larger additions.

6. Suggested Payment Schedule

| Milestone | When | Amount |
| --- | --- | --- |
| Advance to start work | Day 1 (kick-off) | PKR 18,000 (30%) |
| Mid-project payment | Day 7 patient registration, doctor slip, and all billing counters working | PKR 24,000 (40%) |
| Final payment | Day 14 completion, testing, and handover/training | PKR 18,000 (30%) |
| Total |  | PKR 60,000 |

7. Estimated Timeline: 2 Weeks

The full 300 hours of work will be delivered in 2 weeks (14 days) instead of the usual 10–12 weeks.

Day-by-day plan:

| Days | Focus |
| --- | --- |
| 1–2 | Setup, screen design, logins, patient registration & search |
| 3–5 | Doctor registration, doctor slip/token, and all 5 billing counters (Lab, X-Ray, ECG, ECO, Ultrasound) built in parallel |
| 6–9 | Operation Theater module, price/test management, expenses & salaries |
| 10–12 | Management dashboard, speed optimization, and full testing |
| 13–14 | Fixes from testing, staff training, and handover |

⚠️ What a 2-week delivery requires (please note):

Compressing 3 months of work into 2 weeks doesn't reduce the work itself, it means several people build different parts at the same time instead of one developer going step by step. For this to work smoothly:

- A small team (3–4 developers) works in parallel, not a single developer the total cost (PKR 60,000) and total hours (300) stay the same either way.

- Doctors, tests, and prices do not need to be prepared in advance those screens are part of the build, and Management enters real data directly into the system once it's live.

- Same-day feedback is needed at each review point (Day 5, Day 9, Day 12) - a few days' delay on your end pushes the final date by the same amount.

- Access to your cloud server should be ready before Day 10, so deployment/testing on the real environment isn't delayed.

- Testing time is tighter than a normal-paced project, so the first week of real clinic use should be watched closely for minor issues (covered under the free maintenance month).

- Any scope changes mid-way (a new field, a new report) is treated as a new feature request (Section 5), not squeezed into the 2 weeks.

8. A Few Things to Confirm Before We Start

These don't change the price, just help us build it right the first time and with a 2-week timeline, these are needed on Day 1, not later:

- Cash only, or also card/bank payments?

- Printer type for receipts (small counter printer or regular A4 printer)

- Your cloud server details/access, so we can deploy and test on it before final handover (deployment effort is quoted separately see Section 4)

Not needed from you:

- Doctor list, test names, or prices Management registers/updates all of these directly inside the system; nothing needs to be prepared or handed over in advance.

- Currency options: the system uses PKR only, so there's nothing to decide here.

Total Project Cost: PKR 60,000 (excluding deployment) Includes: full system as described, delivered in 2 weeks, + 1 month free maintenance Excludes: deployment/hosting setup, future new features